## Sheet1
Id | Requirment | User story | Task | Acceptance criteria | Moscow | Story Points
1 | The Hub | There needs to be a system consisting of the main hub, senors, display | 1.1 Do research on the microcontroller 1.2 Do research on the parts compatible with the microcontroller 1.3 start development on a devboard |  | must | 5
2 | Encasing | there needs to be an encasing for the product | 1.1 use a 3d printer to make an encasing 1.2 the encasing needs to be able to be opened and closed 1.3 the parts needs to fit in the encasing and not be loose 1.4 it needs to account for - The wires that go in - The buttons - The display - The RFID reader behind the plastic - It needs to be visible where the rfid is located |  | must | 7
3 | RFID Check in | As a client I want to clock in with my RFID card so that my attendance is automatically registered | 1.1 The RFID communicates with the microcontroller 1.2 The RFID sends each clients data to the microcontroller 1.3 The microcontroller locks in the time |  | must | 3
4 | RFID Check out | As a client I want to clock out with the same RFID card | 1.1 the RFID communicates with the microcontroller and sets the end time |  | must | 1
5 | Touchscreen signature | As a Client, I want to sign in on the touchscreen, so that my attendance is legally confirmed | 1.1 A separate database must be setup 1.2 The clients signatures must be stored here |  | must | 5
6 | points awarding | As an administrative worker I want the points (budget) to be automacally asigned to the the existing website | 1.1 Use the attendance to assign the respective points to the clients in the existing database for the website 1.2 The website must show this data live |  | must | 4
7 | dayparts calcualtion | The attendance needs to be grouped in morning/afternoon dayparts | 1.1 Database must be setup for the attendance 1.2 Its split it too parts, morning and afternoon 1.3 The signature is linked to their respective day 1.4 The microcontroller calculates based on the clocked in time what dayparts a client had attended |  | must | 3
8 | attendance overview | As a admistrative worker I want to export attenance records with signatures so that I can send them to external parties | 1.1 The data from the database must be gathered together in a PDF, for every client. 1.2 The PDF shows - Attandance consisting of dates and dayparts - Their signature |  | must | 8
9 | error feedback | I want visual (led) and audio (buzzer) feedback when clocking in fails, so that I know to try again | 1.1 When holding the card before the RFID sensor, and LED must 1.2 If it clocked in succesfull, the buzzer makes a sound |  | must | 4
10 | system reset | as a technician, I want a reset button, so that I can reboot the device without unplugging power | 1.1 a reset button is mounted and connected to the microcontroller wich +B6:D13restarts the device |  | must | 2
11 | hardware refinement | As a technician, I want to design a custom PCB with the required microconroller so that the system is more copmact reliable and professional | 1.1 Research requirments for migrating to a standalone microcontroller 1.2 create schematic and layout for custom pcb 1.3 Order and the the pcb |  | Should | 15